## Planning
LEEP-MB
Simulation Planning
Updated Jan 21
Objective |  | Strategy | Tasks | Target date | Staff | Progress | Comments
Archetype for Manatoba |  | Use HOT3000 to generate geometry | Generate HOT3000 model |  | Jeff | Not started
|  |  | Upload geometry to svn |  | Jeff | Not started | Alex to decide if we will use current svn or git
|  |  | Modify geo, opr files for optimization |  | Jeff/Alex | Not started
|  |  | Compute technology costs |  | Patric? | Not started | Can Patric help us out here?
|  |  | Incorporate HVAC, AIM-2 files… |  | Jeff/Alex
Deploy optimization |  | Run aws cloud results for near ERS 86, | Define new non-NZEH objective |  | Alex | Not started
|  |  | Update substitute.pl to support new objective |  | Alex | Not started
|  |  | Deploy to AWS |  | Alex | Not started
|  |  | Test & Examine results --- make sure objective is OK |  | Alex | Not started
|  |  | Run optimization |  | Alex | Not started
|  |  | Gather results in tableau |  | Alex/Jeff | Not started
|  |  | Prepare web view |  | Alex/Jeff | Not started
|  |  | Prepare slides for presentation | expected Mar 11 | Alex/Jeff | Not started
F. Sheets: | PV | Use NZEH archetype model | Run substitute.pl for PV, no PV | Feb 3 (?) | Alex | Done
| Passive solar | Use NZEH archetype model | Set up choice file for passive solar |  | Alex | Done
|  |  | Run substitute.pl for passive solar, base case | Feb 3 (?) | Alex | Done
| Adv ventilation ctls | Nothing for now
| On-demand DHW | Use NZEH archetype model | Run base hot water, gas fired instantaneous | Feb 3 (?) | Alex | Done
| Exterior insulation | Use NZEH archetype model | Develop envelope thermal MLC layers |  | Jeff | Done | Need to update esp-r MLC databases for new constructions
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Done
| Exterior mineral wool board | Use NZEH archetype model | Verify if R-values are same as XPS case |  | Patric | Done | Patric to determine of Ext XPS and ext MWB cases are different
|  |  | Run base case, upgrade | Feb 3 (?) |  | DOne
| DWHR | Use OEE spreadsheet | Compute 'adjusted volume credit' |  | Alex | Done
|  |  | Add credits to framework |  | Alex | Done
|  |  | Run base case, upgrade | Feb 3 (?) | Alex | Done
| CCASHP | Use NZEH archetype model | Run base case, upgrade | Feb 3 (?) | Alex | Done
| Advanded framing | Use NZEH archetype model | Develop new MLC layers |  | Jeff | Done | Ask patric to narrow insulaiton cases
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Done
| Advanced windows | Use NZEH archetype model | Run base case, upgrade | Feb 3 (?) | Alex | Done
| Smart thermostats | Nothing for now
| Exterior foundation | Use NZEH archetype model | Develop new MLC layers |  | Jeff | Done
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Done

## LEEP sim numbers
|  |  | Gas cost | 0.2558
|  |  | Elec cost | 0.07183
Scenario |  | Electricity use (kWh/yr) | Gas consumption (m³/yr) | Electrcity savings (kWh/yr) | Gas savings (m³/yr) | Total savings ($/yr
Base case (Alex) |  | 12533 | 2401.6
Base case - soft coat windows |  | 12184.7346 | 2660
Base for HRV |  | 12706.0192 | 2413.9628
Upgrade HRV |  | 12530.2832 | 2383.4005 | 175.7359 | 30.5623 | 20.441
DWHR |  | 11981.232 | 2401.5066 | 551.768 | 0.093392 | 39.6574
Gas instantaneous |  | 8473.4749 | 2786.2837 | 4059.5251 | -384.6837 | 193.1936
PV (5 kw facing south) |  | 6137.5 | 2401.6 | 6395.5 | 0 | 459.3888
Advanced Framing | 2.3 ACH | 12528.6063 | 2383.172 | 4.3937 | 18.428 | 5.0295
| 1.5 ACH | 12491.6146 | 2045.5646 | 41.3854 | 356.0354 | 94.0466
Exterior Foundation |  | 12498.2411 | 2299.3206 | 34.7589 | 102.2794 | 28.6598
Exterior Insulation: | 1.5" | 12490.7048 | 2196.0385 | 42.2952 | 205.5615 | 55.6207
| 2.0" | 12482.548 | 2136.9822 | 50.452 | 264.6178 | 71.3132
| 2.5" | 12477.4865 | 2096.0567 | 55.5135 | 305.5433 | 82.1455
CCASHP |  | 26170.3467 | 0 | -13637.3467 | 2401.6 | -365.2413
Advanced windows | Triple hard coat | 12429.1749 | 2268.2624 | 103.8251 | 133.3376 | 41.5655
| Vs soft coat dbls | 12429.1749 | 2268.2624 | -244.4403 | 391.7376 | 82.6483
Passive Solar | Or: south | 12551.2365 | 2234.1982 | -18.2365 | 167.4018 | 41.5115
| South+overhang | 12430.8857 | 2246.8842 | 102.1143 | 154.7158 | 46.9112
| +Extra windows | 12750.7806 | 2183.4013 | -217.7806 | 218.1987 | 40.1721
| +Overhang &drywall | 12620.0418 | 2187.2077 | -87.0418 | 214.3923 | 48.5893