## Planning
LEEP-MB
Simulation Planning
Updated Jan 21
Objective |  | Strategy | Tasks | Target date | Staff | Progress | Comments
Archetype for Manatoba |  | Use HOT3000 to generate geometry | Generate HOT3000 model |  | Jeff | Not started
|  |  | Upload geometry to svn |  | Jeff | Not started | Alex to decide if we will use current svn or git
|  |  | Modify geo, opr files for optimization |  | Jeff/Alex | Not started
|  |  | Compute technology costs |  | Patric? | Not started | Can Patric help us out here?
|  |  | Incorporate HVAC, AIM-2 files… |  | Jeff/Alex
Deploy optimization |  | Run aws cloud results for near ERS 86, | Define new non-NZEH objective |  | Alex | Not started
|  |  | Update substitute.pl to support new objective |  | Alex | Not started
|  |  | Deploy to AWS |  | Alex | Not started
|  |  | Test & Examine results --- make sure objective is OK |  | Alex | Not started
|  |  | Run optimization |  | Alex | Not started
|  |  | Gather results in tableau |  | Alex/Jeff | Not started
|  |  | Prepare web view |  | Alex/Jeff | Not started
|  |  | Prepare slides for presentation | expected Mar 11 | Alex/Jeff | Not started
F. Sheets: | PV | Use NZEH archetype model | Run substitute.pl for PV, no PV | Feb 3 (?) | Alex | Done
| Passive solar | Use NZEH archetype model | Set up choice file for passive solar |  | Alex | Not started
|  |  | Run substitute.pl for passive solar, base case | Feb 3 (?) | Alex | Not started
| Adv ventilation ctls | Nothing for now
| On-demand DHW | Use NZEH archetype model | Run base hot water, gas fired instantaneous | Feb 3 (?) |  | Not started
| Exterior insulation | Use NZEH archetype model | Develop envelope thermal MLC layers |  | Jeff | Done | Need to update esp-r MLC databases for new constructions
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Done
| Exterior mineral wool board | Use NZEH archetype model | Verify if R-values are same as XPS case |  | Patric | Not started | Patric to determine of Ext XPS and ext MWB cases are different
|  |  | Run base case, upgrade | Feb 3 (?) |  | Not started
| DWHR | Use OEE spreadsheet | Compute 'adjusted volume credit' |  | Alex | Done
|  |  | Add credits to framework |  | Alex | Done
|  |  | Run base case, upgrade | Feb 3 (?) | Alex | Not started
| CCASHP | Use NZEH archetype model | Run base case, upgrade | Feb 3 (?) | Alex | Not started
| Advanded framing | Use NZEH archetype model | Develop new MLC layers |  | Jeff | Done | Ask patric to narrow insulaiton cases
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Not started
| Advanced windows | Use NZEH archetype model | Run base case, upgrade | Feb 3 (?) | Alex | Not started
| Smart thermostats | Nothing for now
| Exterior foundation | Use NZEH archetype model | Develop new MLC layers |  | Jeff | Not started
|  |  | Run base case, upgrade | Feb 3 (?) | Jeff | Not started

## LEEP sim numbers
Scenario | Electricity use (kWh/yr) | Gas consumption (m³/yr) | Electrcity savings (kWh/yr) | Gas savings (m³/yr) | Comments
Base case (Alex) | 12504.024 | 2341.548
Base case (Jeff) | 12393.648 | 2333.664
DWHR | 11967.12 | 2341.548 | 536.904 | 0
PV (5 kw facing south) | 6108.524 | 2341.548 | 6395.5 | 0
Exterior Insulation 1.5" XPS | 12362.112 | 2144.448 | 31.536 | 189.216 | Using Jeff's base
Exterior Insulation 2.5" XPS | 12362.112 | 2049.84 | 31.536 | 283.824 | Using Jeff's base
Exterior Insulation 2" MWB |  |  |  |  | Using Jeff's base
Advanced Framing |  |  |  |  | Using Jeff's base
Exterior Foundation |  |  |  |  | Using Jeff's base